## Slide 1: New Credit Union Charter Process
Operation Cigar Box

## Slide 2: The NCUA has taken 17 steps and created 3 phases (milestones
Operation Cigar Box
Phase 1: Establishing a Proof of Concept
Phase 2: Completing the Charter Application
Phase 3: Submitting the Application Forms for Final NCUA Approval

## Slide 3: Phase 1: Proof of Concept (POC)
Researching and determining the purpose of your PFCU
Deciding who it will serve - Organizational certificate (Appendix B Part 701)
Identifying where it will obtain start-up funding and
Determining whether it has enough “Subscribers” (you need a minimum of seven individuals to present a sworn organization certificate with the name, FOM, par value of shares, subscribers contact info)
Submit POC Form (they provide an online template)
https://ncua.gov/support-services/credit-union-resources-expansion/starting-new-federal-credit-union/federal-credit-union-proof-concept-form
NOTE: The NCUA strives to respond within 60 calendar days of the POC submission date. The NCUA will notify you in writing if the POC is approved and you can proceed to Phase 2.

## Slide 4: Phase 2 - Preparing the Charter Application
Developing and conducting a survey of your PFCU’s potential membership
Analyzing market conditions; determining start-up costs and sources of capital to cover those costs
Developing a business plan; and drafting bylaws* and necessary policies**
The NCUA encourages applicants to use the standard bylaws approved by the NCUA Board. Bylaw amendments outside the scope of those the Board has already approved are rare and require separate approval by NCUA in accordance with Part 701, Appendix A, of NCUA’s Regulations.
https://ncua.gov/files/bylaws/federal-credit-union-bylaws-2020.pdf
** Policies and procedures provided from an in-kind donation from PolicyPro

## Slide 5: Phase 3 - Submitting the Application Forms for Final NCUA Approval
NCUA - 4008 - Organizational certificate
NCUA 4012 - Report of official and agreement to serve
NCUA 9500 - Application and Agreement for Insurance Accounts
NCUA 9501 - Certificate of Resolution

## Slide 6: Then finally…..NCUA Issues Charter! The race to the starting line….
Note: According to Article X of the Federal Credit Union Bylaws, “the Agency may revoke the charter for failure to start operations within 60 days after receipt of the approved organization certificate unless the Agency approves an extension of time.” Any delays in the new federal credit union commencing operations should be communicated by the new federal credit union to its assigned NCUA regional office in writing, with an extension request.

## Slide 7: Phase 1: Proof of Concept
This part is easy enough for the groups to do on their own.

## Slide 8: Purpose and Core Values
The purpose should reflect the credit union’s reason for existing. The core values might include items such as member empowerment or fiscal responsibility.
The charter applicant must be able to demonstrate that potential membership interest is sufficient to provide a reasonable prospect of viability.
Your application should include compelling reasons why the formation of a new credit union is in the best interests of the proposed group.
NOTE: The NCUA strives to respond within 60 calendar days of the POC submission date. The NCUA will notify you in writing if the POC is approved and you can proceed to Phase 2.

## Slide 9: Field of Membership
Your application should identify which type of FOM you are requesting—single common bond, multiple common bond, or community—and describe the specific associational and/or occupational groups or the community you plan to serve.
For example, “Persons who live, worship, work in, or attend school in, and businesses and other legal entities located in Pima County, Arizona.” The NCUA will review each submission to determine whether the proposed FOM meets regulatory requirements.

## Slide 10: Amount and source of start-up capital
The actual costs for chartering and operating a federal credit union vary depending on the unique circumstances in which the PFCU plans to operate. Planned product and service offerings, the delivery mechanisms for products and services, staffing needs, and the proposed FOM all factor into these costs.
At this preliminary stage, the NCUA will review your general plan for obtaining donated funds to start operations and cover operating losses until you are profitable. The NCUA will evaluate the adequacy of your capital plans in detail when you submit pro forma financial projections in Phase 2. If an organizing group is unable to identify a credible funding source, charter approval is unlikely.

## Slide 11: PFCU Subscribers
The NCUA will review each submission to determine whether the organizing group identified at least seven individuals to serve as the PFCU’s subscribers. Ideally, the subscribers will collectively have a sound understanding of or backgrounds in accounting, finance, business, and banking or related fields.
The subscribers are the people responsible for completing the research, establishing the concept of the new credit union, and ultimately applying for a new charter.
The organizing group should designate a primary contact, or organizer (this could be a subscriber or a consultant), to complete the Proof of Concept and submit it to NCUA to start the chartering process.

## Slide 12: Phase 2: Completing the Charter Application
Where we need to provide much assistance

## Slide 13: Activity 1 - Conduct Pre-Planning Activities
Operation Cigar Box

## Slide 14: DESIGN THE SURVEY
Survey and analysis of potential membership - their sample survey has 31 questions! BUT applicants do not have to use it. Here’s what the survey needs to cover:
Level of interest - number of members willing to join immediately and amount of initial deposits we can expect
Types of products/services NEEDED - this is where it falls apart. Not wanted, needed. Cigar box credit union needs: shares, a basic CD, basic checking, small dollar loan (signature) and USED auto loan.
Office horus? Really?
Recruit volunteers to serve as officials and on committees

## Slide 15: ANALYZE THE SURVEY RESULTS
We must analyze and summarize the results. Also conduct a market conditions analysis.
  They require a statistically significant response rate to the survey and describe what that means at length.
From their website: Based on the NCUA’s experience, new credit unions do not generally achieve the “best-case scenario.” Due to several factors, including the length of time between conducting the survey and receipt of a credit union charter, not all persons who express an interest in joining actually join the new credit union. Therefore, the NCUA highly recommends developing a business plan and financial projections using the “most likely scenario” assumptions. You can present other scenarios if you can provide sound statistical support.

## Slide 16: SUMMARIZE THE SURVEY RESULTS
They provide an example:
Keep in mind the NCUA relies heavily on your written analysis of the survey results to obtain a better understanding of the basis and content of the business plan, projections, and assumptions.
Survey Documentation Required
Include the following membership survey information. The NCUA recommends keeping survey forms available for review, if necessary:
  Tally of the membership survey results (do not submit the completed individual survey forms to NCUA unless requested);
  Written analysis of the membership survey results;
  Blank copy of the membership survey form;
  Written explanation of how the membership survey form was distributed; and
  Written explanation of the random sample process used to select who received a survey form.

## Slide 17: CONDUCT A MARKET ANALYSIS
The analysis of market conditions should include geographic, demographic, employment, income, housing, and other economic data. At a minimum, the analysis should answer the following questions:
What financial services and service providers are available to the membership? For example, identify the number of credit unions, banks, savings and loan institutions, check cashing facilities, pawn shops, and/or other alternative financial institutions available.
What type of products do the financial providers offer or not offer?
What is the economic condition of the membership? For example, is the sponsor company growing or downsizing, or is the community considered affluent or low income?
What is the need for a credit union?
Who will be the PFCU’s competitors, and how will the PFCU compete?
The data and analysis performed on the market generally helps the organizing group develop the PFCU’s business plan, marketing plan, projections, and assumptions.

## Slide 18: Obtain and Document Sources of Donated Capital
Donated capital can come in the form of “in-kind donations”
Office space
Loaned executive
Technology Services
Marketing Services
Accounting Services
The more in-kind donations the PFCU receives the lower the required capital.

## Slide 19: Provide Evidence of Sponsor Commitment if Critical to Success
Typically this involves donated office space which could include, internet, phone, utilities, employee benefits, etc.
All of these in-kind donations will reduce the amount of capital needed.

## Slide 20: Establish Relationships with Mentors and Other Supporters
This is where the state leagues can become partners with us.
They get an inquiry from a group, send them to the CUDNC where we will provide support in the form of guidance, templates, resources, credit union veterans, etc.
Once the POC has been approved we will match them with a mentor credit union.
The charters that make it all had a village behind them.

## Slide 21: Activity 2 - Business Plan Development
Operation Cigar Box

## Slide 22: NCUA 4001 - FCU Investigation Report
Form they will complete that investigates the subscribers, outlines all the information that has been obtained in activity 1
Will be part of the final submission for charter application

## Slide 23: Mission Statement
Prepare a brief statement describing the purpose of the PFCU. For example: “It is the purpose of this credit union to promote thrift among its members and create a source of credit for provident and productive purposes.” You can also review existing credit union websites for mission statement examples.
Let ChatGPT do it!

## Slide 24: Products and Services
Based on the results of the membership surveys and available capital and funding, identify the products (such as loans and shares) and services (such as money orders, wire transfers, notary service, debit/ATM cards) to be offered in the first two years and the timing of when they will be made available (upon opening, within 6 or 12 months, end of Year 1 or 2). The offering of products and services at the commencement of operations should be based on what is realistically possible for a newly chartered federal credit union with possibly limited income capacity and resources.

## Slide 25: Goals for Shares, Loans, and Number of Members
This section outlines projections for the dollar amount and number of loans and shares and the number of members for the first two years of operation. The intent of this section is to provide benchmarks upon which the credit union and the NCUA can measure the success of the group and its business plan. The goals should be broken down by each loan and share product type and expressed in annual periods. The goals should agree with the financial projections. Include a discussion of the basis for each goal and identify the section of the membership survey supporting the goal.

## Slide 26: Organizational/Management Plan Addressing Qualifications and Planned Training of Officials and Employees
Officials (board, supervisory committee and credit committee)
Senior Management and Credit Union Staff
Documentation required for organizational/management plan (addressing qualifications and planned training of officials and employees)

## Slide 27: Continuity Plan for Director, Committee Members, and Management Staff
Some potential training topics for officials are:
Board governance;
The board’s duties, powers, and responsibilities;
Financial statements and key financial trends and conditions;
The risks of operating a credit union and how to identify and control these risks;
Economic trends and their effect on the credit union;
Effective business planning with goals and measurable outcomes;
How to conduct effective meetings;
CEO or manager evaluations;
Communicating with other officials and staff effectively; and
Working and communicating with your regulator and insurer.

## Slide 28: Identifying a Physical Location
Each credit union must have at least one physical location, including PFCUs that are anticipating most transactions via the internet, kiosks, or other electronic means. The organizing group should determine an anticipated location of the main office and any other physical branch locations to be open at inception. If the exact addresses are not known, provide the city and state.
Documentation Required for the Identified Location
Document the PFCU’s anticipated physical address of its main office and any branches to be opened at inception, in the business plan.
Provide a draft copy of a lease agreement or other commitment documents as applicable.

## Slide 29: Recordkeeping and Data Processing System
Identify the data processing system(s) the credit union will use. Discuss why the system(s) was selected and the cost of the system(s). Draft copies of the proposed hardware and software purchase or lease agreements, maintenance contracts, and vendor estimates of other ongoing costs should be reviewed by an attorney representing the PFCU’s interest. Include the documents and reviews in your application package. The NCUA will also evaluate if any limitation on the terms of any draft contract would be necessary.1 Incorporate the associated costs (including fixed assets, amortization, depreciation expense, and others) into the pro forma balance sheets and income statements.

## Slide 30: Surety Bond Coverage
Section 713.5 of the NCUA’s Regulations requires minimum bond coverage, currently as shown below.
Total Assets: $0 to $4,000,000 Minimum Bond: Lesser of total assets or $250,000.
Total Assets: $4,000,001 to $50,000,000 Minimum Bond: $100,000 plus $50,000 for each million or fraction thereof over $1,000,000.
Total Assets: $50,000,001 to $500,000,000 Minimum Bond: $2,550,000 plus $10,000 for each million or fraction thereof over $50,000,000, to a maximum of $5,000,000.
Total Assets: Over $500,000,000 Minimum Bond: One percent of assets, rounded to the nearest hundred million, to a maximum of $9,000,000.

## Slide 31: Source of Funds and Other Support
You must ensure the level of funding and support is sufficient to operate the credit union by providing services deemed important by the members, as reflected in the membership survey. The PFCU’s financial projections should include all monetary support and subsidies that are detailed in this section of the business plan. Support can come from any source(s), for example:
A sponsor, organizer, individual, mentor credit union or another financial institution
Grants of donations of capital
Non-member deposits
Donated equipment
Any other in-kind donations or subsidies

## Slide 32: Plans for Operating Independently
You need to explain and support how the PFCU will continue operations after Year 2 while remaining solvent (showing positive net worth).1 Include assumptions in this section and provide support in the form of annual pro forma financial projections (including balance sheet and income statement projections) demonstrating when the PFCU will generate positive net income absent grants or donations from outside sources. Submit pro forma financial projections that extend through the year positive net income is achieved.
1 Net worth is computed as all the credit union’s retained earnings, including undivided earnings, regular reserves, uninsured secondary capital (available for LID credit unions only), net income, and other reserves (excluding the allowance for loan and lease losses, and accumulated gains/losses on available for sale securities).

## Slide 33: Develop a Marketing Plan
Documentation Required for the Marketing Plan
Discuss what activities and events are planned within the PFCU’s service area and/or groups to promote the new federal credit union’s services and products. For example, participation in local Chamber of Commerce events, such as a vendor fair or annual food drive.
As part of the business plan, submit a written marketing plan including costs associated with each marketing initiative as detailed in this section.
They actually provide a template example of a marketing calendar - it’s horrible.

## Slide 34: Create Pro Forma Financial Statement Projections and Assumptions
NCUA provides an example of detailed pro forma financial statement projections.
Before finalizing the pro forma financial statement projections and assumptions, the PFCU should confirm with NCUA that the review of the membership survey was found to be adequately completed (represents a statistically valid random sample or targeted random sample, the results are tallied, and a written analysis developed).
Once the results from the membership survey are tallied, analyzed, and conclusions reached, you will use the results to develop assumptions for membership, loans, shares, usage of products and services, etc. and projections for the PFCU’s pro forma financial statements.

## Slide 35: Activity 3 - Adopt Proposed Bylaws
Operation Cigar Box

## Slide 36: NCUA Provides the Bylaws
Establish Proposed Credit Union Bylaws
Customize the NCUA’s Federal Credit Union Bylaws within the parameters the NCUA Board has preapproved, to meet the needs of the PFCU. Fill in the indicated blanks and select the appropriate options available for certain articles or sections. No other changes can be made to the bylaws without prior NCUA approval.
Documentation Required for Bylaws
Provide to CURE by email the adopted credit union bylaws.

## Slide 37: Activity 4 - Draft Proposed Policies
Operation Cigar Box

## Slide 38: LeagueInfoSight has given us free access to CU Policy Pro
Free access to policies and procedures from CU PolicyPro®
CU PolicyPro® is an online system with more than 230 detailed model policies and procedures to help credit unions manage today’s ongoing compliance and operational challenges.
In addition to the model content, CU PolicyPro includes a comprehensive policy management system! The system includes a beautiful, modern, and easy-to-navigate design to help all users easily find, view, and print both model policies and the credit union’s own customized policies. System administrators and policy editors have a whole toolbox to create, maintain and distribute policies, assign and track policy updates and reviews, upload and share additional documents, view and confirm relevant model policy updates, and manage user access to the policy level.

## Slide 39: Phase 3: Submitting the application forms for final NCUA approval
This is the final step and again, easy enough to do on their own.

## Slide 40: All of these forms on on their website
NCUA - 4008 - Organizational certificate
NCUA 4012 - Report of official and agreement to serve
NCUA 9500 - Application and Agreement for Insurance Accounts
NCUA 9501 - Certificate of Resolution